## schedule_data
Activity_ID | WBS | Activity_Name | Discipline | Area | Contractor | Baseline_Start | Baseline_Finish | Forecast_Finish | Actual_Start | Actual_Finish | Planned_Percent | Actual_Percent | Float_Days | Critical_Flag | Reporting_Date
A100 | WBS-01 | Site Clearing | Civil | Area A | Contractor A | 2024-01-01 | 2024-01-10 | 2024-01-10 | 2024-01-02 | 2024-01-11 | 100 | 100 | 1 | No | 2024-06-01
A101 | WBS-01 | Foundation Works | Civil | Area B | Contractor A | 2024-01-11 | 2024-01-25 | 2024-01-28 | 2024-01-12 |  | 100 | 92 | -3 | Yes | 2024-06-01
A102 | WBS-02 | Steel Erection | Structural | Area A | Contractor B | 2024-02-01 | 2024-02-20 | 2024-02-25 | 2024-02-03 |  | 100 | 88 | -5 | Yes | 2024-06-01
A103 | WBS-03 | Equipment Setting | Mechanical | Area B | Contractor C | 2024-02-15 | 2024-03-05 | 2024-03-12 | 2024-02-16 |  | 85 | 70 | -7 | Yes | 2024-06-01
A104 | WBS-04 | Pipe Rack Installation | Piping | Area C | Contractor D | 2024-03-01 | 2024-03-25 | 2024-03-31 | 2024-03-02 |  | 75 | 61 | -6 | Yes | 2024-06-01
A105 | WBS-05 | Cable Tray Installation | Electrical | Area C | Contractor E | 2024-03-10 | 2024-04-01 | 2024-04-05 | 2024-03-12 |  | 68 | 59 | -2 | No | 2024-06-01
A106 | WBS-06 | Instrument Hook-Up | Instrumentation | Area B | Contractor F | 2024-03-20 | 2024-04-15 | 2024-04-22 | 2024-03-21 |  | 54 | 46 | -4 | No | 2024-06-01
A107 | WBS-04 | Hydrotest Preparation | Piping | Area C | Contractor D | 2024-04-01 | 2024-04-20 | 2024-04-28 | 2024-04-02 |  | 45 | 33 | -8 | Yes | 2024-06-01
A108 | WBS-03 | Pump Alignment | Mechanical | Area B | Contractor C | 2024-04-05 | 2024-04-25 | 2024-05-02 | 2024-04-06 |  | 40 | 29 | -6 | No | 2024-06-01
A109 | WBS-02 | Steel Touch-Up | Structural | Area A | Contractor B | 2024-04-10 | 2024-04-22 | 2024-04-23 | 2024-04-11 |  | 50 | 46 | -1 | No | 2024-06-01
A110 | WBS-05 | Power Cable Pulling | Electrical | Area C | Contractor E | 2024-04-12 | 2024-05-03 | 2024-05-10 | 2024-04-15 |  | 39 | 28 | -5 | Yes | 2024-06-01
A111 | WBS-06 | Loop Checking Prep | Instrumentation | Area B | Contractor F | 2024-04-20 | 2024-05-15 | 2024-05-18 | 2024-04-21 |  | 32 | 24 | -3 | No | 2024-06-01

## milestones
Milestone_ID | Milestone_Name | Discipline | Baseline_Date | Forecast_Date | Actual_Date | Status | Owner
M01 | Civil Completion | Civil | 2024-06-15 | 2024-06-18 |  | Watch | Civil Lead
M02 | Structural Completion | Structural | 2024-06-25 | 2024-06-29 |  | At Risk | Structural Lead
M03 | Mechanical Completion | Mechanical | 2024-07-20 | 2024-07-29 |  | At Risk | Mechanical Lead
M04 | Piping Hydrotest | Piping | 2024-07-30 | 2024-08-06 |  | At Risk | Piping Lead
M05 | Electrical Energization | Electrical | 2024-08-10 | 2024-08-12 |  | Watch | Electrical Lead
M06 | Ready for Commissioning | Multi | 2024-08-25 | 2024-09-05 |  | At Risk | Project Manager

## evm_data
Date | WBS | PV | EV | AC
2024-01-01 | WBS-01 | 60000 | 56000 | 54000
2024-02-01 | WBS-01 | 120000 | 110000 | 108000
2024-03-01 | WBS-02 | 250000 | 220000 | 235000
2024-04-01 | WBS-03 | 390000 | 340000 | 350000
2024-05-01 | WBS-04 | 520000 | 470000 | 455000
2024-06-01 | WBS-05 | 650000 | 590000 | 575000
2024-06-01 | WBS-06 | 720000 | 670000 | 640000

## progress_data
Date | Discipline | Area | Installed_Qty | Total_Qty | Planned_Progress | Actual_Progress
2024-06-01 | Civil | Area A | 950 | 1000 | 100 | 95
2024-06-01 | Civil | Area B | 880 | 1000 | 98 | 88
2024-06-01 | Structural | Area A | 780 | 900 | 92 | 87
2024-06-01 | Mechanical | Area B | 620 | 1000 | 85 | 70
2024-06-01 | Piping | Area C | 550 | 900 | 75 | 61
2024-06-01 | Electrical | Area C | 430 | 700 | 68 | 59
2024-06-01 | Instrumentation | Area B | 300 | 650 | 54 | 46

## risk_data
Risk_ID | Area | Discipline | Risk_Type | Risk_Description | Risk_Score | Delay_Days | Constraint_Status | Owner
R01 | Area B | Mechanical | Material | Equipment delivery lag | 9 | 7 | Open | Mechanical Lead
R02 | Area C | Piping | Construction | Low weld productivity | 8 | 6 | Open | Piping Lead
R03 | Area C | Electrical | Procurement | Cable tray shortage | 6 | 4 | Mitigated | Electrical Lead
R04 | Area B | Instrumentation | Engineering | Late IFC drawings | 7 | 5 | Open | Instrument Lead
R05 | Area A | Structural | Construction | Crane availability issue | 5 | 3 | Watch | Structural Lead
R06 | Area B | Civil | Construction | Concrete rework at foundation block | 4 | 2 | Mitigated | Civil Lead

## progress_curve
Period | Planned_Progress | Actual_Progress | Forecast_Progress
Jan-2024 | 8 | 7 | 7
Feb-2024 | 18 | 16 | 16
Mar-2024 | 30 | 27 | 28
Apr-2024 | 44 | 40 | 41
May-2024 | 55 | 50 | 52
Jun-2024 | 62 | 58 | 60
Jul-2024 | 72 | 67 | 70
Aug-2024 | 86 | 80 | 84
Sep-2024 | 100 | 94 | 100

## Relationships
POWER BI RELATIONSHIP MAP
From Table | From Column | To Table | To Column | Notes
schedule_data | WBS | evm_data | WBS | Many-to-many may exist in sample data; in a polished model, use a Dim_WBS table.
schedule_data | Discipline | progress_data | Discipline | Better practice: use Dim_Discipline.
schedule_data | Area | progress_data | Area | Better practice: use Dim_Area.
schedule_data | Discipline | risk_data | Discipline | Better practice: use Dim_Discipline.
schedule_data | Area | risk_data | Area | Better practice: use Dim_Area.
Calendar | Date | evm_data | Date | Create Calendar table in Power BI.
Calendar | Date | progress_data | Date | Create Calendar table in Power BI.
Calendar | Date | schedule_data | Reporting_Date | Create Calendar table in Power BI.

## DAX_Measures
STARTER DAX MEASURES
Measure Name | DAX Formula | Purpose | Format
Planned Progress % | Planned Progress % = AVERAGE(schedule_data[Planned_Percent]) | Top KPI card for planned completion | 0.0% or 0
Actual Progress % | Actual Progress % = AVERAGE(schedule_data[Actual_Percent]) | Top KPI card for actual completion | 0.0% or 0
SPI | SPI = DIVIDE(SUM(evm_data[EV]), SUM(evm_data[PV])) | Schedule Performance Index | 0.00
CPI | CPI = DIVIDE(SUM(evm_data[EV]), SUM(evm_data[AC])) | Cost Performance Index | 0.00
Schedule Variance | Schedule Variance = SUM(evm_data[EV]) - SUM(evm_data[PV]) | EV minus PV | #,##0
Cost Variance | Cost Variance = SUM(evm_data[EV]) - SUM(evm_data[AC]) | EV minus AC | #,##0
Forecast Delay Days | Forecast Delay Days = AVERAGEX(schedule_data, DATEDIFF(schedule_data[Baseline_Finish], schedule_data[Forecast_Finish], DAY)) | Average schedule slippage in days | 0
Critical Activities | Critical Activities = CALCULATE(COUNTROWS(schedule_data), schedule_data[Critical_Flag] = "Yes") | Count of critical activities | 0
Delayed Milestones | Delayed Milestones = COUNTROWS(FILTER(milestones, milestones[Forecast_Date] > milestones[Baseline_Date])) | Count of slipped milestones | 0
Activities Behind Plan | Activities Behind Plan = COUNTROWS(FILTER(schedule_data, schedule_data[Actual_Percent] < schedule_data[Planned_Percent])) | Count activities under plan | 0
Average Float Days | Average Float Days = AVERAGE(schedule_data[Float_Days]) | Average total float | 0.0
Progress Variance % | Progress Variance % = [Actual Progress %] - [Planned Progress %] | Headline variance KPI | 0.0% or 0
Installed Progress % | Installed Progress % = DIVIDE(SUM(progress_data[Installed_Qty]), SUM(progress_data[Total_Qty])) * 100 | Optional construction KPI | 0.0% or 0